## Sample SDLC plan
FY-2023
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Analysis and Planning | bar: Q1 Jan
Requirment Gathering | bar: Q1 Feb to Q1 Mar
Design and Prototyping | bar: Q2 Apr to Q2 May
Software Development | bar: Q2 Jun to Q3 Aug
QA Testing | bar: Q3 Sep
UAT Testing | bar: Q4 Oct
Deployment | bar: Q4 Nov
Maintainance and Updates | bar: Q4 Nov to Q4 Dec

## Sample Detail Plan
Y-Mart Project Timelines
WBS Number |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Status | Priority | Task description | Cost/Efforts | Actual cost/Efforts | Dependency
1 | Project Management Activities |  |  | 2023-03-14 | 2023-03-15 |  | 0 | 16 | 0 |  |  |  | 0 | 0
1.1 |  | Project Charter |  | 2023-03-14 | 2023-03-14 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
1.2 |  | Project Management Plan |  | 2023-03-15 | 2023-03-15 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
1.3 |  | Monitoring/Controlling Activities |  | 2023-03-14 | 2023-03-14 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
2 | Initiation/Planning |  |  | 2023-03-14 | 2023-03-17 |  | 0 | 24 | 0 |  |  |  | 0 | 0
2.1 |  | Feasibility Study |  | 2023-03-14 | 2023-03-14 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
2.2 |  | Business Case |  | 2023-03-15 | 2023-03-15 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
2.3 |  | Project Planning |  | 2023-03-16 | 2023-03-16 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
2.4 |  | Initiation/Planning Activities Completed |  | 2023-03-17 | 2023-03-17 |  | 0 | 0 | 0 | Open | Medium |  | 0 | 0
3 | Requirements Analysis |  |  | 2023-03-17 | 2023-03-21 |  | 0 | 16 | 0 |  |  |  | 0 | 0
3.1 |  | Requirements Gathering |  | 2023-03-17 | 2023-03-17 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
3.2 |  | Security Planning |  | 2023-03-18 | 2023-03-18 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
3.3 |  | Requirements Analysis Completed |  | 2023-03-21 | 2023-03-21 |  | 0 | 0 | 0 | Open | Medium |  | 0 | 0
4 | Design |  |  | 2023-03-21 | 2023-03-24 |  | 0 | 32 | 0 |  |  |  | 0 | 0
4.1 |  | High-Level Design |  | 2023-03-21 | 2023-03-21 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
4.2 |  | Proof of Concept |  | 2023-03-22 | 2023-03-22 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
4.3 |  | Detailed Design |  | 2023-03-23 | 2023-03-23 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
4.4 |  | Technical Specification |  | 2023-03-24 | 2023-03-24 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
4.5 |  | Design Completed |  | 2023-03-24 | 2023-03-24 |  | 0 | 0 | 0 | Open | Medium |  | 0 | 0
5 | Development |  |  | 2023-03-25 | 2023-04-08 |  | 0 | 88 | 0 |  |  |  | 0 | 0
5.1 |  | Build/Develop |  | 2023-03-25 | 2023-03-28 |  | 0 | 16 | 0 | Open | Medium |  | 0 | 0 | Secure the liscenses
5.2 |  | Integration Planning |  | 2023-03-30 | 2023-03-30 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0 | Get the Third party dev environment details
5.3 |  | Documentation |  | 2023-03-31 | 2023-03-31 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
5.4 |  | Test Planning |  | 2023-03-25 | 2023-03-25 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
5.5 |  | Deployment Planning |  | 2023-04-01 | 2023-04-01 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0 | Engange Operations team
5.6 |  | Training Planning |  | 2023-04-04 | 2023-04-06 |  | 0 | 24 | 0 | Open | Medium |  | 0 | 0
5.7 |  | Business Continuity Planning |  | 2023-04-07 | 2023-04-07 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
5.8 |  | Transition Planning |  | 2023-04-08 | 2023-04-08 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
5.9 |  | Development Completed |  | 2023-04-08 | 2023-04-08 |  | 0 | 0 | 0 | Open | Medium |  | 0 | 0
6 | Testing |  |  | 2023-04-11 | 2023-04-21 |  | 0 | 64 | 0 |  |  |  | 0 | 0
6.1 |  | Unit Test |  | 2023-04-11 | 2023-04-11 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
6.2 |  | Function Test |  | 2023-04-12 | 2023-04-12 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
6.3 |  | Integration Test |  | 2023-04-13 | 2023-04-15 |  | 0 | 24 | 0 | Open | Medium |  | 0 | 0
6.4 |  | Regression Test |  | 2023-04-18 | 2023-04-18 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
6.5 |  | System Test |  | 2023-04-19 | 2023-04-19 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
6.6 |  | User Acceptance Test |  | 2023-04-20 | 2023-04-20 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
6.7 |  | Test Completed |  | 2023-04-21 | 2023-04-21 |  | 0 | 0 | 0 | Open | Medium |  | 0 | 0
7 | Deployment |  |  | 2023-04-21 | 2023-04-26 |  | 0 | 24 | 0 |  |  |  | 0 | 0
7.1 |  | Deployment |  | 2023-04-21 | 2023-04-21 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
7.2 |  | Training |  | 2023-04-22 | 2023-04-25 |  | 0 | 16 | 0 | Open | Medium |  | 0 | 0
7.3 |  | Support |  | 2023-04-25 | 2023-04-25 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
7.4 |  | Development/Implementation Completed |  | 2023-04-26 | 2023-04-26 |  | 0 | 0 | 0 | Open | Medium |  | 0 | 0
8 | Operations & Maintenance |  |  | 2023-04-26 | 2023-04-29 |  | 0 | 24 | 0 |  |  |  | 0 | 0
8.1 |  | Operations Activities |  | 2023-04-26 | 2023-04-26 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
8.2 |  | Maintenance Activities |  | 2023-04-27 | 2023-04-27 |  | 0 | 8 | 0 | Open | Medium |  | 0 | 0
8.3 |  | Operations & Maintenance Completed |  | 2023-04-29 | 2023-04-29 |  | 0 | 0 | 0 | Open | Medium |  | 0 | 0

## Development
Epics/Timelines | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  | 2023-06-01 |  |  |  | 2023-07-01
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
User Management | bar: 2023-03-01 Week 1
Product Catalog Management | bar: 2023-03-01 Week 1 to 2023-03-01 Week 2
Shopping Cart Management | bar: 2023-03-01 Week 2
Order Management | bar: 2023-03-01 Week 3 to 2023-03-01 Week 4
Shipping and Delivery Management | bar: 2023-03-01 Week 4 to 2023-04-01 Week 2
Payment Gateway Integration
Analytics and Reporting | bar: 2023-03-01 Week 3 to 2023-04-01 Week 1
Wishlist and Save for Later Management | bar: 2023-04-01 Week 2 to 2023-04-01 Week 3
Product Recommendations and Personalization | bar: 2023-04-01 Week 1 to 2023-04-01 Week 4
Social Media Integration and Marketing | bar: 2023-04-01 Week 4 to 2023-05-01 Week 2
Customer Support and Service | bar: 2023-05-01 Week 1 to 2023-05-01 Week 4
Multi-language and Multi-currency Support | bar: 2023-05-01 Week 2 to 2023-06-01 Week 2
Inventory and Warehouse Management | bar: 2023-06-01 Week 1 to 2023-06-01 Week 3
Returns and Refunds Management | bar: 2023-06-01 Week 3 to 2023-07-01 Week 2
Gift Card and Voucher Management | bar: 2023-06-01 Week 4
Affiliate and Referral Program Integration | bar: 2023-06-01 Week 4 to 2023-07-01 Week 1
Loyalty and Rewards Program Integration | bar: 2023-07-01 Week 1 to 2023-07-01 Week 2
Sales and Discounts Management
Email Marketing and Newsletter Management | bar: 2023-07-01 Week 2 to 2023-07-01 Week 3
Mobile App Development and Integration | bar: 2023-07-01 Week 4
Security and Fraud Prevention | bar: 2023-07-01 Week 3 to 2023-07-01 Week 4
Accessibility and User Experience Improvement | bar: 2023-07-01 Week 1 to 2023-07-01 Week 4